## Sheet1
System Name: Online Grocery System
Members:
Derick Wayne Batucan | A
Kent Delos Cientos | B
Vic Andre Bacusmo | C
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Project Proposal and approval |  | 2024-09-11 | 2024-09-11 | Approved
2. Figma (login Page) | B | 2024-09-23 |  | In-Progress
3. User Profile | B
4. Product Browsing and Search | B
5. Shopping Cart Management | A
6. Order Placement and Checkout | A
7. Payment Integration | B
8. Order History and Reordering | B